## Sheet1
GROUP 2: STARSHIP STRIKERS
S. NO. | TASK NAME | MEMBERS | ASSIGNED ROLES | REG - SAP ID | START DATE | END DATE | DURATION | DEPENDENCY | PROGRESS | REVIEWS & APPROVAL
1 | PROJECT PLANNING AND FINALIZATION | WALEED ABBASI | PROJECT MANAGER | 55550 - 32819 | 2023-12-29 16:00 | 2024-01-01 18:00 | 3 Days | NONE | COMPLETED
2 | SOFTWARE REQUIREMENTS SPECIFICATIONS (SRS) | MUHAMMAD AFFAN ABBASI | BUSINESS ANALYST | 52884 - 29174 | 2023-12-29 16:00 | 2024-01-01 18:00 | 3 Days | NONE | COMPLETED
3 | UI/UX | MUHAMMD HAMZA | UI/UX DESIGNER | 52879 - 28317 | 2024-01-02 22:00 | 2024-01-08 18:00 | 1 Week | BA | COMPLETED
4 | Build APP UI | MUHAMMAD HARIS | APP FRONTEND | 51379 - 31342 | 2024-01-08 22:00 | 2024-01-15 18:00 | 1 Week | BA / UI | COMPLETED
5 | Fundamental Structures | MUHAMMAD HARIS | APP FRONTEND | 51379 - 31342 | 2024-01-08 22:00 | 2024-01-15 18:00 | 1 Week | BA / UI | COMPLETED
6 | Tabs | MUHAMMAD HARIS | APP FRONTEND | 51379 - 31342 | 2024-01-08 22:00 | 2024-01-15 18:00 | 1 Week | BA / UI | COMPLETED
7 | Buttons | HAMZA IMRAN | APP FRONTEND | 54668 - 32095 | 2024-01-08 22:00 | 2024-01-15 18:00 | 1 Week | BA / UI | COMPLETED
8 | Enables Frontend Functionalities in Different Buttons | HAMZA IMRAN | APP FRONTEND | 54668 - 32095 | 2024-01-08 22:00 | 2024-01-15 18:00 | 1 Week | BA / UI / DEV | COMPLETED
9 | Develop News Section Layout | HAMZA IMRAN | APP FRONTEND | 54668 - 32095 | 2024-01-08 22:00 | 2024-01-15 18:00 | 1 Week | BA / UI / DEV | COMPLETED
10 | Frontend & Backend Connectivity Support | MUHAMMAD HARIS | APP FRONTEND | 51379 - 31342 | 2024-01-08 22:00 | 2024-01-22 18:00 | 2 Week | BA / UI / DEV | COMPLETED
11 | Web Scraping | DILZAIB | APP BACKEND | 54655 - 32037 | 2024-01-08 22:00 | 2024-01-22 18:00 | 2 Week | BA / UI / DEV | COMPLETED
12 | Mongodb | DILZAIB | APP BACKEND | 54655 - 32037 | 2024-01-08 22:00 | 2024-01-22 18:00 | 2 Week | BA / UI / DEV | COMPLETED
13 | API | ANDREW INAYAT | APP BACKEND | 53138 -27915 | 2024-01-08 22:00 | 2024-01-22 18:00 | 2 Week | BA / UI / DEV | COMPLETED
14 | Frontend & Backend Connectivity Support | MUHAMMAD MAAZ ALI KHAN | APP BACKEND | 53083 - 29359 | 2024-01-08 22:00 | 2024-01-22 18:00 | 2 Week | BA / UI / DEV | COMPLETED
15 | Software Testing | ASIM ALI | TESTER | 58454 - 26884 | 2024-01-22 22:00 | 2024-01-25 18:00 | 3 Days | BA / DEV | COMPLETED
16 | Project Submission & Viva | All | All | All | 2024-01-26 13:00 | 2024-01-26 18:00 | 1 Day | ALL | TO BE HELD